## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 4 | 4 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 4 | 3.2 | 0.8 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 6 | 3.6 | 2.4 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 6 | 2.4 | 3.6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 7 | 1.4 | 5.6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 4 | 4 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 8 | 6.4 | 1.6 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 3 | 1.8 | 1.2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 5 | 2 | 3 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 5 | 5 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 2 | 1.6 | 0.4 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 5 | 3 | 2 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 4 | 1.6 | 2.4 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 4 | 0.8 | 3.2 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 10 | 10 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 6 | 4.8 | 1.2 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 7 | 4.2 | 2.8 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 2 | 0 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
KRAAG Courses ++
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Website - related
| Learn react | 2019-10-25 | 2019-10-28 | 2 | All | 100% | bar: WEEK 1 F to WEEK 2 F
| Backend | 2019-10-25 | 2019-11-04 | 7 | Grant | 100% | bar: WEEK 1 F to WEEK 3 M
| Dropdown filter | 2019-10-28 | 2019-11-04 | 6 | Antonette | 100% | bar: WEEK 2 M to WEEK 3 M
| Front page / list view | 2019-10-28 | 2019-11-04 | 6 | Rikki | 100% | bar: WEEK 2 M to WEEK 3 M
| Search bar | 2019-10-28 | 2019-11-04 | 6 | Alfonso | 100% | bar: WEEK 2 M to WEEK 3 M
| Modal | 2019-10-28 | 2019-11-04 | 6 | Karen | 100% | bar: WEEK 2 M to WEEK 3 M
Documentation and other items
| Documentation | 2019-10-30 | 2019-11-04 | 4 | All | 100% | bar: WEEK 2 M to WEEK 3 M
| UML | 2019-11-01 | 2019-11-04 | 2 | Alfonso / Karen | 100% | bar: WEEK 2 M to WEEK 3 M
| Gantt Chart | 2019-10-25 | 2019-11-04 | 7 | Antonette | 99% | bar: WEEK 1 F to WEEK 3 M
| Team meeting logs | 2019-10-25 | 2019-11-04 | 7 | All | 100% | bar: WEEK 1 F to WEEK 3 M
| Scrum Artifacts | 2019-10-25 | 2019-11-04 | 7 | Alfonso | 100% | bar: WEEK 1 F to WEEK 3 M
Future Items
| Report Feature | 2019-11-16 | 2019-11-30 | 10 | Rikki | 100%
| Adding tags to answers | 2019-11-16 | 2019-11-30 | 10 | Karen | 100%
| Delete classes / resources | 2019-11-16 | 2019-12-01 | 10 | Antonette | 100%
| Backend | 2019-11-16 | 2019-12-01 | 10 | Grant | 100%
| Add users | 2019-11-16 | 2019-12-01 | 10 | Alfonso | 100%
Documentation and other items
| Documentation | 2019-11-11 | 2019-12-01 | 15 | All | 100%
| UML | 2019-11-12 | 2019-12-01 | 14 | Alfonso / Karen | 100%
| Gantt Chart | 2019-11-11 | 2019-12-01 | 15 | Antonette | 100%
| Team meeting logs | 2019-11-14 | 2019-12-01 | 12 | All | 100%
| Scrum Artifacts | 2019-11-15 | 2019-12-01 | 11 | Alfonso | 100%
| Test Suite | 2019-11-15 | 2019-12-01 | 11 | All | 100%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])